CREATING A NEW EDUCATIONAL PROGRAM AT NWIC

FLOW OF PROCESS

Consult with either the Dean of Academics and Distance Learning or with the Director of Outreach and Community Education to begin the process. See the forms and instructions for each phase for more detail about the process.

# Text boxes

Activities:

Develop -

*Curriculum material

*Financial projection

*Calendar for implementation

Approximate time to complete = 1-3 months

Approve Program

Phase 2

Evaluate Program

Gather and Analyze Data

Program of Study or

Award of Completion:

Route to Dean of Academics and Distance. Learning

Training Program

Route to Director of Outreach and Community Education

Activities:

*Administrators and faculty evaluate

*Select SPA

Approximate time to complete = 1 month

Phase 1

Phase 3

Develop Curriculum

Implement Program

Phase 4

Phase 5

Phase 6

Phase 7

Activities:

*SPA oversees data gathering and analysis

*SPA for program determination team

Approximate time to complete = 1- 3 months

Activities:

*Program determination team evaluates feasibility

*Team recommends approval or disapproval and type of program

Approximate time to complete = 1 month

Activities:

Approvals and submissions vary by type of program: *Curric. Com.

*Vice President

*Admin. Team

*NWIC Board

*Federal Financial Aid

* NWCCU

Approximate time to complete for program of study or award of completion = 1-2 months

Training programs require Director of Outreach and Community Education approval only.

Activities:

*Marketing

*Recruit students

*Program Dev.

*Hire faculty

*Orientation

*Offer courses and program

Approximate time to complete for program of study or award of completion = 2 months or start of next qtr.

Approximate time to complete for training program = 1 month or less

Activities: *Evaluation plan

*Formative and summative Assessment

*Evaluation and * Recommend

*Reevaluation timeline

Approximate time to complete = one program cycle

Propose
Program

Determine Feasibility